## Backlog
Product Backlog |  | 0/47 completed | See "Instructions" tab for guidance if needed.
✓ | Member | Task Name (Feature) | User-Story (create one if needed) -- Format : “As a type of user, I want functionality so that reason.” | MoSCoW Priority | Satus
FALSE | Serina | Create database with sample inventory | "As a developer, I want to access sample data so that I may use it for application development and testing."
FALSE | Serina | Implement secure login/registration with email and password | "As a customer, I want to create an account with my email and password so that I can securely access the ordering system and track my orders" | Must | Not Started
FALSE | Serina | Create order history for customers | "As a customer, I want to view my previous orders so that I can reorder my favorites quickly." | Must | Not Started
FALSE | Serina | Create interface for managing supplier information and contacts | "As a business owner, I want to maintain a list of my suppliers so that I can easily place orders when needed." | Must | Not Started
FALSE | Serina | Configure continuous integration and deployment pipeline | "As a developer, I want integration tests so that I can catch bugs early and ensure code reliability" | Should | Not Started
FALSE | Serina | Create setup guide for local development environment | "As a developer, I want clear setup instructions so that I can quickly get the project running on my machine" | Should | Not Started
FALSE | Serina | Enable ordering without account creation (enable guest check-out) | "As a first-time customer, I want to place an order without creating an account that I can quickly make a purchase" | Should | Not Started
FALSE | Tristin | Export sales summaries as spreadsheets | "As a business owner, I want to save sales reports in a more convenient and portable format." | Should | Not Started
FALSE | Tristin | Create customer and admin UI concept | "As a frontend developer, I want an example of what the user interface should look like. | Should | Not Started
FALSE | Tristin | Discuss team member roles and responsibilites | "As a team member, I want an idea of what aspects of development I should focus on, as well as team strengths and weaknesses." | Should | Not Started
FALSE | Tristin | Review and finalize project scope | "As a team member, I want to adapt the SRS to new team realities and create a greater sense of ownership." | Should | Not Started
FALSE | Tristin | Review and finalize project architecture | "As a team leader, I want to understand the high-level design to choose appropriate technologies and delegate tasks." | Must | Not Started
FALSE | Tristin | Review and finalize development environment / technologies / languages | "As a developer, I want to use technologies that fascilitate the product architecture." | Must | Not Started
FALSE | Tristin | Organize the Product Backlog by sprint (Lesson 3 Agile Product Backlog Due 2/2) | "As a developer, I want to quickly determine which backlog items are relevant to the current sprint." | Must | Not Started
FALSE | Tristin | Create the Project Development Plan (Lesson 3 Due 2/2) | "As a team leader, I want an up-to-date document outlining the project and development strategies." | Must | Not Started
FALSE | Kenny | Product browsing interface | As a customer, I want to browse available products or menu items so that I can decide what I want to order. | Must | Not Started
FALSE | Kenny | Order item customization | As a customer, I want to customize items in my order (such as extras or options) so that my order matches my preferences. | Must | Not Started
FALSE | Kenny | Order submission and status tracking | As a customer, I want to submit my order and see its current status so that I know when it is being prepared or completed. | Must | Not Started
FALSE | Kenny | Update and manage inventory levels | As a business owner, I want to update inventory quantities in real time so that customers cannot order items that are out of stock. | Must | Not Started
FALSE | Kenny | Manage products and pricing | As a business owner, I want to add, edit, or remove products and prices so that my menu stays accurate. | Must | Not Started
FALSE | Kenny | View sales summaries | As a business owner, I want to view daily or weekly sales summaries so that I can track performance and identify trends. | Should | Not Started
FALSE | Kenny | Role-based user permissions | As a system administrator, I want to restrict access based on user roles so that customers and business users can only access features relevant to them. | Must | Not Started
FALSE | Kim | Implement password reset and account recovery | As a registered user, I want to reset my password so that I can regain access if I forget my credentials. | Must | Not Started
FALSE | Kim | Implement email verification after account creation | As a system administrator, I want users to verify their email so that accounts are legitimate and secure. | Must | Not Started
FALSE | Kim | Add audit logging for critical system actions | As a developer, I want important actions logged so that system issues can be diagnosed and reviewed. | Should | Not Started
FALSE | Kim | Implement accessibility improvements (ARIA labels, keyboard navigation) | As a user with accessibility needs, I want the application to be usable with assistive technologies. | Should | Not Started
FALSE | Kim | Implement basic search for products or orders | As a user, I want to search lists so that I can quickly find specific items. | Must | Not Started
FALSE | Kim | Create user help or FAQ page for ordering system | As a customer, I want access to a help or FAQ page so that I can quickly find answers if I have questions while ordering. | Should | Not Started
FALSE | Kim | Add empty-state and loading-state UI messaging | As a user, I want clear feedback when data is loading or unavailable so that the system feels responsive. | Should | Not Started
FALSE | Rachel | Implement product detail view with item descriptions and pricing | As a customer, I want to view detailed information about a product so that I can understand what I’m ordering before I customize or add it to my cart. | Should | Not Started
FALSE | Rachel | Create administrative dashboard homepage with key metrics | As a business admin, I want to upload a CSV file of products so that I can quickly populate or update my product catalog without entering items one by one. | Should | Not Started
FALSE | Rachel | Add low‑stock notifications for business admins | As a business admin, I want to filter orders by date, status, or customer so that I can easily find the orders I need to review or manage. | Must | Not Started
FALSE | Rachel | Build product category filtering for browsing interface | As a user, I want the system to automatically log me out after a period of inactivity so that my account and personal information remain secure. | Should | Not Started
FALSE | Rachel | Implement order confirmation and receipt screen | As a business admin, I want to view a log of system actions so that I can track changes made to products, inventory, and settings. | Must | Not Started
FALSE | Rachel | Add logging and display of order status timeline | As a customer, I want to cancel my order while it is still pending so that I am not charged or committed to an order I no longer want. | Could | Not Started
FALSE | Rachel | Create admin settings page for business configuration | As a business admin, I want to configure tax rates and service fees so that order totals reflect my business’s pricing and legal requirements. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Tyler | Documentation And Presentation | As a deal for documentation I will create the slides. | Must | Not Started
FALSE | Caleb | Database / System-Oriented | As a customer, I want my in-progress order to be saved automatically, so that I don’t lose my selections if the app refreshes or closes unexpectedly. | Must | Not Started
FALSE | Caleb | Inventory Transaction Logging | As a business owner, I want all inventory changes (sales, restocks, manual edits) logged with timestamps, so that I can audit stock discrepancies and track inventory history. | Should | Not Started
FALSE | Caleb | Order Status History Tracking | As a business admin, I want each order’s status changes to be recorded in the database, so that I can review how long orders stay in each stage (Pending, In Progress, Ready, Completed). | Must | Not Started
| Caleb | Data Validation at Database Level | As a system administrator, I want the database to enforce constraints (non-negative inventory, valid prices, required fields), so that invalid or corrupt data cannot be stored. | Must | Not Started
| Caleb | Soft Deletion of Products | As a business owner, I want products to be soft-deleted instead of permanently removed, so that historical orders referencing those products remain intact. | Should | Not Started
| Caleb | User Role Enforcement in Data Access | As a system, I want database queries to respect user roles (customer vs business admin), so that users can only access data they are authorized to see. | Must | Not Started
| Caleb | Automated Low-Stock Flagging | As a business owner, I want the system to automatically flag low-inventory items based on configurable thresholds, so that I can restock before items sell out. | Could | Not Started

## Instructions
Product Backlog Instructions
Step 1: | Team Member Name ¦ Column B | Each team member must contribute at least 7 unique tasks or features to this list by 7 pm on Thursday 1/29.
Step 2: | Task Name (Feature) ¦ Column C | Add a feature or a task that will be add progress or value to our project development.
Step 3: | User Story ¦ Column D | Write or include the user story that would be associated with that task. Please use the format provided: “As a type of user, I want functionality so that reason.”
Step 4: | MoSCoW Priority (NEW!) | For YOUR contributed item(s), add MoSCoW priority: - M = Must Have (core functionality) - S = Should Have (important but not critical) - C = Could Have (nice to have) - W = Won't Have (this semester)
TIPS | - Reference the Orderly SRS Documentation called “Group 9 SRS V2.docx” - Your name next to this task does NOT mean that you are responsible for it. It is there to account for your added contribution to the backlog. - Some features/tasks will share the same user story. That’s okay. - Types of users include: Customer, Business Owner, Employee, Developer, etc.